## Sheet1
ID | Type | User Story / Task | Priority | Assignee | Status | Acceptance Criteria
PBI‑01 | Feature | As a visitor, I want a homepage so that I see who Wealthy Pillars is immediately. | High | Theodore | To Do | Homepage displays site title, mission and a hero section, responsive on mobile.
PBI‑02 | Feature | As a visitor, I want an About page so I understand organization’s purpose. | High | Erastus | To Do | About page with mission, team bios, values.
PBI‑03 | Feature | As a client, I want a Services page so I see what offerings are available. | High | Erastus | To Do | Services listed with descriptions, well styled.
PBI‑04 | Feature | As a user, I want Contact Us form so I can reach out easily. | High | Theodore | To Do | Form fields (name, email, message), submission confirmation.
PBI‑05 | Feature | As admin, I want site navigation bar and footer so that UX is consistent. | Medium | Theodore | To Do | Navbar and footer present on all pages, links work correctly.
PBI‑06 | Feature | As owner, I want privacy policy & terms of use pages. | Medium | Erastus | To Do | Legal pages accessible via footer links.
PBI‑07 | Feature | As visitor, I want blog page to view articles (optional). | Low | Either | Backlog | Blog posts list view, click through individual posts if needed.
PBI‑08 | Technical | Set up repository wealthypillarsglobalnetwork.github.io. | High | You | Done | Repo created, Pages enabled, sample index works.
PBI‑09 | Technical | Enable HTTPS and custom domain (if available). | Medium | You | To Do | HTTPS enforced, custom domain resolves.
PBI‑10 | Technical | Set up local development process (Git + VS Code workflow). | High | You | To Do | Code commits and pushes reflect live site changes.
PBI‑11 | Technical | Add Google Analytics tracking snippet (optional). | Low | You/Erastus | Backlog | Tracking code included in template, indexing visible in Analytics dashboard.
PBI‑12 | Technical | Ensure site is responsive on desktop and mobile. | High | Both | In Progress | Layout adapts smoothly across device sizes; manually tested.
PBI‑13 | Technical | Optimize images and assets for fast page load. | Medium | Both | In Progress | Pages load under 3 seconds; image sizes are optimized.
PBI‑14 | Bug | Fix any broken links or missing images before launch. | High | Both | To Do | No 404 errors; all assets load correctly.
PBI‑15 | Maintenance | Add README file in repo explaining purpose and how to update site. | Medium | You | To Do | README.md includes basic instructions for editing/publishing.